## Year End Closing Process
Activity/Task |  | Staff Responsible | Prior Activities |  | Fiori | Year End Close Day | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
|  |  |  | TCODE | Tile |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Notes
Year End Close Activities
Purchasing Activities
1.1 | Shopping Carts - start analysis of year end shopping carts. Can shopping carts be created for the new year at a certain point in time rather than in period 12 | Purchasing
1.2 | Last day to create a shopping cart (and approve) | Purchasing
1.3 | Open Purchase Requisitions for Shopping Carts in New Year, Value Type 50 only | Sustainment office/Finance Group |  | FMIR | Open Periods in FM
1.4 | Purchase Orders - Start Analysis of Purchase Orders. Can purchase orders be crdeated for the new year at a certain point in time rahter than in period 12 | Purchasing
1.5 | Last day to create a purchase order (and approve) | Purchasing
1.6 | Last day to receive goods
1.7 | Last day to submit an invoice (and approve)
1.8 | Determine Purchase Orders that should not carryforward 1. Takes necessary actions to ‘close’ these orders 2. Options: a. GR: set final GR flag b. IR: set final IR flag c. Reduce purchase order to match qty / amount ‘received / invoiced / paid’ | Purchasing
1.9 | Maintain GR/IR Account (Analyze and Clear) | Purchasing |  | MR11 | Clear GR/IR Accounts
1.10 | Analysis of Funds commitments to determine if close or carryforward | Sustainment office/Finance Group |  | FMRP_RFFMEP1OX | Commitments
1.11 | Analysis Fund Reservations determine if close or carryforward | Sustainment office/Finance Group |  | FMRP_RFFMEP1OX | Commitments
1.12 | Run Commitment/Actual Report for all open encumbrances and review by department | Sustainment office/Finance Group |  | FMRP_RFFMEP1AX | All Postings
1.13 | Add configuration to allow carry forward of budget for commitments for the year being closed | Sustainment office/Finance Group |  | SPRO: Public Sector => Funds Management => Closing Operations => Closing Operations for BCS =>Define budget carry forward for commitment | N/A
1.14 | Add configuration to define budget document setting for the budget for commitment carry forward | Sustainment office/Finance Group |  | SPRO: Public Sector => Funds Management => Closing Operations => Closing Operations for BCS => Define budget entry documents for commitment carry forward | N/A
Posting Period Control
2.1 | Open New Budget Year | Sustainment office/Finance Group |  | FMBOSTAT
2.2 | Open FI Posting Period 1 | Sustainment office/Finance Group |  | OB52 | Open and Close Posting Periods
2.3 | Open Period 1 for Posting | Sustainment office/Finance Group |  | OKP1 | Open CO Periods
2.4 | Open MM Period for New Month Period 1 | Sustainment office/Finance Group |  | MMPV | Close MM Periods
2.5 | Review Changes to MM Period | Sustainment office/Finance Group |  | MMRV | Allow Postings to Previous MM Period | [16 empty] | Currently All Value Types Are Open
2.6 | Open Posting Periods in FM for New FY | Sustainment office/Finance Group |  | FMIR | Open Periods in FM
2.7 | Open Budget Periods in FM for all budget versions | Sustainment office/Finance Group |  | FMOPER | [17 empty] | LD requires that only one period can be open CO
2.8 | Lock users out of the system - This will prevent errors for the FM carryforward processes | [20 empty] | LD requires that only one period can be open CO
2.9 | Full system backup
2.10 | Unlock the users performing the FM carryforwards
2.11 | Carryfoward Commitments (Purchase Orders) | Sustainment office/Finance Group |  | FMJ2 or FMJC_D | Year-End Closing: Carryfoward Commitments or Carryfoward Commitments According to Entry Date
2.12 | Carryfoward Commitments (Funds Reservations) | Sustainment office/Finance Group |  | FMJ2 or FMJC_D | Year-End Closing: Carryfoward Commitments or Carryfoward Commitments According to Entry Date
2.13 | Carryfoward Commitments (Funds Commitments) | Sustainment office/Finance Group |  | FMJ2 or FMJC_D | Year-End Closing: Carryfoward Commitments or Carryfoward Commitments According to Entry Date | [16 empty] | Currently All Value Types Are Open
2.14 | Reverse Commitment Carryforward | Sustainment office/Finance Group |  | FMJ3 | Reverse Commitment Carryforwards
2.15 | Manual Zero Carryfoward | Sustainment office/Finance Group |  | FMJ0 | Manual Zero Carryforward | [16 empty] | LD requires that only one period can be open CO
2.16 | FM Obligation Closeout (for funds reservations and funds commitments only) | Sustainment office/Finance Group |  | FMMC | FM Obligation (Funds Res) Closeout
2.17 | Carryforward Residual Budget | Sustainment office/Finance Group |  | FMMPCOVR | Carryover Residual Budget
2.18 | Validate FM Obligation Close out | Sustainment office/Finance Group |  | FMRP_RFFMEP1AX | All Postings
2.19 | Validate the Budget Carryforward | Sustainment office/Finance Group |  | ???
2.20 | Allow users back in the system | [20 empty] | Currently All Value Types Are Open
| Create AUC Subassets prior to settlement | Property Inventory
| Perform IO Settlements -Test Mode, resolve errors | Property Inventory
| Perform IO Settlements -Update Mode | Property Inventory
| Perform Project Settlements - Test Mode, resolve errors | Property Inventory
| Perform Project Settlements - Update Mode | Property Inventory
| Reconcile Settlement Postings | Property Inventory
| Reconcile Settlement Postings | Property Inventory
| Run Directory of Unposted Asset List | Property Inventory
| Run Incomplete Asset List | Property Inventory
| Run Report to identify asset with a value and no capitalization date as of the last day of the previous FY | Property Inventory
| Ensure that all Asset Downpayments have invoices posted | Property Inventory
| Recalculate Asset Depreciation | Property Inventory
| Run Depreciation for Period 12 - Test Mode | Property Inventory
| Run Depreciation for Period 12 - Update Mode | Property Inventory
Close Asset Year (2 yrs prior) TEST MODE ONLY
CANNOT PROCEED TO FI CARRYFORWARD UNTIL THE ABOVE STEPS FOR ASSETS AND SETTLEMENTS ARE COMPLETED
| Carryforward FI Balances and open Asset Year (formerly fiscal year change) |  |  | Balance Carryforward
Month End Close for June
Cash and Investments
2.1 | Review Bank Reconciliation Status | Financial Reporting |  | FTE_BSM | Bank Statement Monitor
2.2 | Perform clearing for bank and other cash transactions | Financial Reporting |  | FEBAN | Reprocess Bank Statement Items
2.3 | Review Cash Position | Treasury |  | FF7AN | Cash Position
2.4 | Book month/year end valuation - Investments | Treasury |  | TPM1 | Run Valuation
2.5 | Book month/year end interest accruals - Bonds | Treasury |  | TPM44 | Run Accrual/Deferral
2.6 | Book month/year end interest accruals - Term loans | Treasury |  | TPM44 | Run Accrual/Deferral
2.7 | Book month end amortizations - COI/Underwriters discount | Treasury |  | TPM44 | Run Accrual/Deferral
2.8 | Book month end buy in for Endowments | Student Financial Services |  | FB50 | Post General Ledger Entries
2.9 | Execute Year End Valuatoins for Investments | Treasury |  | TPM1 | Run Valuation
AP Items in Workflow
3.1 | Post any leftover vendor invoices | Accounting Operations |  | FB60 / MIRO | Create Incoming Invoices/ Enter Incoming Invoices
3.2 | Upload PO Based Invoices | Accounting Operations |  | ZAP_UPLOAD_POBASED | Custom AP PO Mass Upload Program
3.3 | Upload NON-PO Based Invoices | Accounting Operations |  | ZAP_UPLOAD_NONPO | Custom AP Non-PO Mass Upload Program
3.4 | Upload One-Time Invoices | Accounting Operations |  | ZAP_UPLOAD_ONETIME | Custom AP Non-PO Mass Upload Program
3.5 | Review items in Workflow and approve if applicable to the month being closed | Accounting Operations |  | INBOX | My Inbox
Fixed Assets Downpayments
4.1 | Monitor down payment | Purchasing |  | ME2DP | Downpayment Monitoring for PO
4.2 | Post down payment request | Purchasing |  | F-47 | Supplier Down Payment Request
4.3 | Clear down payment | Purchasing |  | F-48 | Clear Supplier Down Payment
Payment Runs
5.1 | Execute payment runs and generate outputs | Accounting Operations |  | F110 (automatic) / F-53 (manual) | Schedule Automatic Payments
5.2 | Generate positive pay file for the prior month | Accounting Operations |  | FCHX or ZFCHX | Positive Pay
5.3 | Close FI Period 12 for Vendor Invoices (type K) | Sustainment Office |  | OB52 | Open and Close Posting Period
Accounts Receivable items in Workflow
6.1 | Post any leftover customer invoices | Central Accounts Receivable |  | FB70 | Customer INvoice
6.2 | Upload customer invoices | Central Accounts Receivable |  | ZFI_ARUPLOAD | AR Invoice Mass Upload
6.3 | Review items in Workflow and approve if applicable to the month being closed | Central Accounts Receivable |  | INBOX | My Inbox
6.4 | Close FI Period 12 for Customer Invoices (type D) | Sustainment Office |  | OB52 | Open and Close Posting Period
Recurring Documents
7.1 | Create and Save Recurring Entries | FO Central Office |  | FBD1 | Enter Recurring Entry
7.2 | Review/Display Recurring Entry Documents to ensure they are appropriate/correct before being run at month end | FO Central Office |  | FBD3 | Display Recurring Entry
7.3 | Display Recurring Entry Details | Sustainment |  | F.15 | List of Recurring Entry Documents
7.4 | Create Batch Job for Posting Documents for Recurring Entries | Sustainment |  | F.14 | Execute Recurring Entry Posting
7.5 | Process Batch Job | Sustainment |  | SM35 | Batch Input Session Overview
Accrual Entries
8.1 | Create accrual entries and review | FO Central Office |  | FB50 or | Post General Ledger Entries
8.2 | Create and post accruals and deferrals | FO Central Office |  | FBS1 | Enter Accrual/Deferral Entry
8.3 | Reverse accruals / deferrals from the prior month | FO Central Office |  | F.81 | Reverse Accrual Deferral Document
8.4 | Review accruals and deferrals posted/reversed | FO Central Office |  | FAGLL03H/GL Trans Report | GL Line item Display GL View
Month End Journal Entries
9.1 | Create and Post Month End Journal Entries | FO Central Office |  | FB50 | Post General Ledger Entries
9.2 | Create and Post Month End Journal Entries | FO Central Office |  | ZFI_JVUPLOAD | ZFI_JVUPLOAD / JV Upload from File
9.3 | Direct blll Joutnal entries | FO Central Office |  | ZFI_JVUPLOAD | ZFI_JVUPLOAD / JV Upload from File
9.4 | Month end accrual entries | FO Central Office |  | FB50 | Post General Ledger Entries
9.5 | Review items in Workflow and approve if applicable to the month being closed | FO Central Office |  | INBOX | My Inbox
9.6 | Review the balance in GL9999999 to ensure it is zero.... this is the JVUPLOAD clearing GL | Sustainment |  | FAGLL03H/GL Trans Report | GL Line item Display GL View
Workflow Documents FI AP AR not Approved
| Review custom parked document report | Sustainment
| Reject parked documents | Sustainment
| Allow users to change date and resubmit or delete | Sustainment
| Mass Delete Parked Documents FI/AP | Sustainment |  | ZFI_PARK_MASS_DEL
Clearing Entries
10.1 | Process Automatic Clearing for Vendors, Customers and OIM GLs except GRIR account | Accounting Operations/Central AR |  | F.13 | Automatic Clearing
10.2 | Process Automatic Clearing for GRIR Account separately from step above | Accounting Operations/Central AR |  | F.13 | Automatic Clearing
10.3 | Clear Customers Manually if needed | Central AR/Research Accounting |  | F-32 | Clear Customer
10.4 | Clear Vendors Manually if needed | Accounting Operations |  | F-44 | Clear
10.5 | Clear OIM GLs Manually if needed | Central AR |  | F-03
10.6 | Treasury Clearing activities outside FEBAN | Treasury |  | ??
10.7 | Maintain GR/IR Account (Analyze and Clear) | Procurement |  | MR11 | Clear GR/IR Accounts
Asset Closing
11.1 | Ensure that all Asset Downpayments have invoices posted and block from depreciation if not cleared. | Property Inventory |  | ME2DP | Downpayment Monitoring for PO
11.2 | Create AUC Subassets prior to settlement | Property Inventory |  | AS11_FMIM
11.3 | Perform IO Settlements -Test Mode, resolve errors | Property Inventory |  | KO8G | Actual IO Settlement: Projects/Networks
11.4 | Perform IO Settlements -Update Mode | Property Inventory |  | KO8G | Actual IO Settlement: Projects/Networks
11.5 | Perform Project Settlements - Test Mode, resolve errors | Property Inventory |  | CJ8G / CJ88H | Actual Settlement: Projects/Networks
11.6 | Perform Project Settlements - Update Mode | Property Inventory |  | CJ8G / CJ88H | Actual Settlement: Projects/Networks
11.7 | Reconcile Settlement Postings | Property Inventory |  | KOB1 | Display Cost Line Items Report - Orders - Actual
11.8 | Reconcile Settlement Postings | Property Inventory |  | CJI3 | Project Actual Cost Line Items
11.9 | Run Directory of Unposted Asset List | Property Inventory |  | S_ALR_87012056 | Directory of Unposted Assets
11.10 | Run Incomplete Asset List | Property Inventory |  | AUVA | FI-AA Incomplete Assets
11.11 | Run Report to identify asset with a value and no capitalization date as of the last day of the previous FY | Property Inventory |  | AR01 | Call Asset List
11.12 | Recalculate Asset Depreciation | Property Inventory |  | AFAR
11.13 | Run Depreciation - Test Mode | Property Inventory |  | AFAB | Depreciation
11.14 | Run Depreciation - Update Mode | Property Inventory |  | AFAB | Depreciation
11.15 | Close FI Period for Assets (Type A) | Sustainment Office |  | OB52 | Open and Close Posting Periods
Burden Program
12.1 | Post Burdens - Retro Program | Research Accounting |  | ZFI_BURDENCALC | ZFI_BURDENCALC | [16 empty] | As needed for rate updates
12.2 | Post Burdens - Daily program | Sustainment |  | ZFI_BURDENCALC_DB | ZFI_BURDENCALC_DB
12.3 | Post Burdens - Cash Basis Program | Research Accounting |  | ZFI_BURDENCALC_CB | ZFI_BURDENCALC_CB
Grant Closing
13.1 | Review and release billing documents to accounting | Research Accounting |  | VFX3 | Release Billing Documents for Accounting
13.2 | Review items yet to be billed | Research Accounting |  | VF04 | Maintain Billing Due List (RRB Mass)
13.3 | Block or unblock grant line items | Research Accounting |  | GM_BLOCK_STATUS | GM Resource-Related Billing-Block/Unblock Line Items for Billing
13.4 | Execute grant billing (RRB, Periodic and Milestone billing) | Research Accounting |  | GM_RRB_IND/GM_RRB_MASS | GM Resource-Related Billing-Individual Grant / GM Resource-Related Billing-Multiple Grants
13.5 | Run Grant Line Item Report to Review Billings/Grants | Research Accounting |  | S_PLN_16000269 | GM Line Item Report
13.6 | Run Project Line Item Actuals Report | Research Accounting |  | CJI3 | Project Actual Cost Line Items
13.7 | Run Line Item Actuals Report for Orders | Research Accounting |  | KOB1 | Display Cost Line Items Report - Orders - Actual
Revenue Recognition
14.1 | Post Revenue Recognition thru EOM/EOY | FO Central Office |  | ZFI_REVACCR | Automated Revenue Recognition
Posting Period Control
15.1 | Close FI Posting Period for the month | Sustainment |  | OB52 | Open and Close Posting Periods
15.2 | Close CO Period for the month | Sustainment |  | OKP1 | Open CO Period
Year End Closing Steps
| Update TVARVC for months and year settings | Sustainment
| Carryforward customer balances - Test Mode | Sustainment |  | F.07
| Run customer line item report | Sustainment |  | FBL5N
| Carryforward customer balances - Update Mode | Sustainment |  | F.07
| Carryforward vendor balances - Test Mode | Sustainment |  | F.07
| Run vendor line item report | Sustainment |  | FBL1N
| Carryforward vendor balances - Update Mode | Sustainment |  | F.07
| Close Asset Year - Test Mode | Sustainment |  | AJAB
| Close Asset Year - Update Mode | Sustainment |  | AJAB
| Validate Closed Asset Year | Sustainment |  | OAAQ/SE16N
| Close CO Periods 1-12 | Sustainment |  | OKP1
| Close FI Period for GL Accts pd12, open pd 13 | Sustainment |  | OB52
| Close FI Periods for Customers, Vendors, Assets pd 13-16 | Sustainment |  | OB52
| Close FM Periods | Sustainment |  | FMIR
Processing in Special Period 13-16
15.1 | Post Entries in Special Periods |  |  | FB50 | Park GL Account Document
15.2 | Post Entries in Special Periods |  |  | ZFI_JVUPLOAD | Upload JE
Various Reports
| Reconciliation Reports: Trial Balance |  |  | Various
| Reconciliation Reports: AR |  |  | Various
| Reconciliation Reports: AP |  |  | Various
| Reconciliation Reports: Assets |  |  | Various
| Reconciliation Reports: Budget Vs Actual |  |  | Various
| Reconciliation Reports: Procurement |  |  | Various